## Sheet1
EXAMPLE
RISK AND MITIGATION PLAN
SYSTEMS DEVELOPMENT AND DESIGN
[7 empty] | Rating Scale | Impact Rating
[7 empty] | 1 | No Impact
2
[7 empty] | 3 | Some Impact
4
[7 empty] | 5 | Material Impact
[7 empty] | 6 | Severe
7
8
[7 empty] | 9 | Business Failure
10
Status Key
[7 empty] | Totally Unacceptable | Jeopardy
[7 empty] | Unacceptable | High
[7 empty] | Reasonably Acceptable | Medium
[7 empty] | Acceptable | Low
[7 empty] | The Project | Date
Development of an Internal Instant Messaging APP
FEASIBILITY and RISK ANALYSIS
Technical Feasibility: Can We Build It?
Area of Concern | Risk # | Risk Description | Probability | Impact | Rating | Risk Category
Technical Feasibility: Can We Build It? | 1 | Description of familiarity with Functional area | 7 | 8 | 56% | Medium
| 2 | Description of familiarity with Technology | 3 | 6 | 18% | Low
| 3 | Description of Project Size | 8 | 9 | 72% | High
| 4 | Description of Compatibility | 4 | 7 | 28% | Low
Economic Feasibility: Should We Build It? | 1 | Description of Tangible Costs and Benefits | 6 | 9 | 54% | Medium
| 2 | Description of Intagible Costs and Benefits | 7 | 8 | 56% | Medium
Organisational Feasibility: If We Build It Will They Come? | 1 | Description of Strategic Alignment | 4 | 7 | 28% | Low
| 2 | Description of User Acceptance | 6 | 7 | 42% | Medium